## Sheet1
FRIENDS OF DARWEN CEMETERY
WORKING PARTY REPORT 2022
Dates | Volunteer Numbers | Volunteer Hours | Running Total Hours | Sections worked on | Work Carried Out
JANUARY
8th January | 7 | 7 |  | D1 | Rhododendron hedge trimmed
22nd January | 11 | 32.15 |  | D1, Nature garden, F, A | Rhododendron hedge trimmed Brambles removed Holly Tree trimmed Chippings moved to sunken graves
3 Thursdays | 7 | 60 |  | K, A, 5A, 2, 5 | Brambles removed, headstones and grave surrounds uncovered and reset, Chippings move to sunken graves
|  | 99.15 | 0
FEBRUARY
5th February | 10 | 28.1 |  | G, 5/F | Path edges cleared and drains unblocked, Fallen trees overhanging paths trimmed back
19th February | 6 | 6 |  | General | General check for fallen trees following stormy weather and high winds
4 Thursdays | 10 | 118 |  | A, 5A, 2, 5 D K, G B | Headstones and grave surrounds uncovered and reset, chippings moved to sunken graves, path edges raised and reset, sunken section of path adjacent to D1 filled (in preparation for tarmacking) Brambles removed storm damaged trees and old stumps removed
|  | 152.1 | 251.25
MARCH
5th March | 11 | 32 |  | G, | Graves cleared in preparation for the re-erection of headstones
19th March | 10 | 20.15 |  | General | Grave Maintenance
4 Thursdays | 10 | 144 |  | 5 G 5 and 5A General | 2 sessions spent burning the waste Brambles and other invasive plants removed 2 grave refurbishments General maintenance and fallen tree removal
|  | 196.15 | 447.4
APRIL
2nd April | 7 | 18 |  | G | Grave plots cleared
16th April | 10 | 28 |  | G | Grave plots cleared
3 Thursdays, 1 abandoned due to wind and rain | 9 | 71 |  | A, 5A, K Memorial wall | Headstones and grave surrounds uncovered and reset, Grave plots cleared Swept
|  | 117 | 564.4
MAY
30th April | 6 | 16 |  | 5 G | Fallen tree removed Grave plots cleared
14th May | 5 | 14 |  | 3 | Cleared path edges
4 Thursdays | 8 | 84 |  | A, 5A, K Memorial wall Prickly Corner | Headstones and grave surrounds uncovered and reset, Grave plots cleared Swept Weeded
|  | 114 | 678.4
JUNE
28th May | 6 | 15 |  | Ashton memorial | Weeded
11th June | 11 | 33 |  | General | Grave Maintenance
25th June | 9 | 26 |  | Ashes garden | Weeded flower beds and mulched with bark chippings
5 Thursdays | 8 | 103 |  | A,5A Lark Street A,C Memorial wall Prickly corner | Headstones and grave surrounds uncovered and reset, Lime suckers removed Path edges cleared Swept Weeded
|  | 177 | 855.4
JULY
9th July | 10 | 29 |  | Nature garden | Clear path edges and cut grass
23rd July | 10 | 28 |  | 5 Nature garden | Balsam bashing Weeding and path edges
4 Thursdays | 7 | 76 |  | A A,C Ashes garden Military section | Headstones and grave surrounds uncovered and reset Path edges cleared Grass mowed Grass mowed
|  | 133 | 988.4
AUGUST
6th August | 10 | 29.3 |  | South Lodge Main entrance | Privet Hedges trimmed Hedges trimmed and flower beds weeded
20th August | 14 | 33.3 |  | Lark Street Section 3 | Lime suckers and brambles reoved Self seeded willow trees cut back
5 Thursdays | 8 | 106 |  | A 2 4 5a J Memorial Wall Ashes Garden Nature Garden Lark Street | Headstones and grave surrounds uncovered and reset Grass mowed and graves refurbished Grave refurbised for entry into Grave maintenance scheme Graves refurbished Balsam removed Brushed and hedge trimmed Grass mowed Flower beds weeded Lime suckers removed
|  | 169 | 1157.4
SEPTEMBER
3rd Sept | 11 | 26.35 |  | Section 4 | Invasive trees cut back
17th Sept | 11 | 32.15 |  | General | Grave Maintenance
3 Thursdays | 7 | 63 |  | A 2 5a J Heather Bed | Headstones and grave surrounds uncovered and reset Grass mowed and graves refurbished Graves refurbished Balsam removed Ferns cut back and bark chippings spread
|  | 121.5 | 1279.2
OCTOBER
1st Oct | 12 | 34 |  | Section G Memorial wall | Invasive trees cut back, Graves cleared for refurbishment New steps started opposite the Memorial Wall for easy and safe across to Section G Swept
15th Oct | 9 | 22.3 |  | Section G Memorial wall | Invasive trees cut back, Graves cleared for refurbishment Continued work on new steps opposite the Memorial Wall for easy and safe across to Section G Swept
4 Thursdays | 6 | 68 |  | A 2 Section G | Headstones and grave surrounds uncovered and reset Grass mowed and graves refurbished Graves refurbished and continued work on new steps opposite the Memorial Wall for easy and safe across to Section G
|  | 124.3 | 1403.5
NOVEMBER
29th Oct | 8 | 21 |  | Section G Memorial wall | New steps completed Area prepared for remembrance day services, flags brushed and bark chippingd laid down over mud
12th Nov | 10 | 27 |  | Section H | Trim back and remove brambles and willow herb to reveal graves.
2th Nov | 12 | 28 |  | Section H | Trim back and remove brambles and willow herb to reveal graves.
4 Thursdays | 6 | 61 |  | A Section G Section H | Headstones and grave surrounds uncovered Preparation work for remembrance services Trim back and remove brambles and willow herb to reveal graves
|  | 137 | 1540.5
DECEMBER
10th Dec | 12 | 34.15 |  | General | Grave Maintenance
3 Thursdays | 5 | 28 |  | A Section H | Headstones and grave surrounds uncovered Trim back and remove brambles and willow herb to reveal graves
|  | 62.15 | 1603.05